PROJECT SCOPE DOCUMENT

Warehouse Operations & Profitability Analysis

NorthCrest Dairy  |  Analytics Project

| Project Title | Warehouse Operations & Profitability Analysis |
| --- | --- |
| Client / Company | NorthCrest Dairy (anonymized) |
| Analyst | Maj Okrikri |
| Date | May 2026 |
| Status | In Progress |
| Tools | Microsoft Excel, Microsoft Power BI |
| Dataset Period | January 2023 - December 2025 (3 years) |
| Data Source | Internal warehouse ERP export (synthetic / anonymized) |

1.  Business Problem

NorthCrest Dairy's warehouse operations currently lack centralized visibility into three critical performance areas: product profitability, order fulfillment quality, and inventory cost management. Without a consolidated view of these areas, operations managers cannot quickly identify which product categories are generating losses, where shipment delays are concentrated, or which inventory lines carry disproportionate storage costs.

This analysis addresses that gap by building a data-driven performance layer on top of the warehouse's existing transactional data. The output will allow leadership and operations teams to move from reactive decision-making to proactive, evidence-based management.

2.  Project Objectives

- Quantify profitability at the product and category level across the full three-year dataset.

- Measure and monitor on-time shipment performance by product category and customer region.

- Identify seasonal and year-over-year trends in sales volume and revenue.

- Analyse warehouse inventory levels and storage cost efficiency over time.

- Deliver audience-specific dashboards that translate data into operational decisions.

3.  Scope

In Scope

- Three years of transactional order data (2023 - 2025), across all product categories.

- Inventory and storage cost data for all SKUs tracked in the warehouse system.

- Fulfillment performance data including order completion times and delay flags.

- All customer regions: Western Canada, Central Canada, and Atlantic Canada.

- All sales channels: Retail, Foodservice, and Industrial.

Out of Scope

- Raw production data, supplier contracts, and procurement costs are not included.

- Individual customer-level PII is excluded; analysis uses Customer ID references only.

- Predictive or machine learning models are not part of this project phase.

- Financial statements, balance sheets, or full P&L reconciliation are not in scope.

4.  Stakeholders

The following stakeholders will be the primary consumers of the project deliverables:

| Stakeholder | Role | Decisions They Make | What They Need |
| --- | --- | --- | --- |
| VP of Operations | Senior Leadership | Budget allocation, product line strategy, market prioritization | High-level profitability view, trend direction, regional performance summary |
| Warehouse Manager | Operations | Daily fulfillment priorities, inventory reordering, delay reduction | Fulfillment rate by SKU, storage cost breakdowns, inventory level alerts |

5.  Analytical Questions

This project is designed to answer the following five questions:

- Profitability by product:  Which product categories and individual SKUs generate the highest and lowest profit margins, and which products are running at a net loss after storage costs?

- Sales trends over time:  How have net sales and order volume trended month over month and year over year, and are there identifiable seasonal patterns in buying behaviour?

- Shipment performance:  What is the on-time delivery rate by product category and customer region, and where are shipment delays most concentrated?

- Inventory and storage efficiency:  How do warehouse inventory levels and storage costs change across months and product categories, and which SKUs carry a disproportionate storage burden relative to their sales contribution?

- Customer and market segmentation:  Which customer markets (Retail, Foodservice, Industrial) and geographic regions drive the most order volume and revenue, and how does purchasing behaviour differ across them?

6.  Metrics to Track

| Metric | Definition / Formula | Analytical Question Answered |
| --- | --- | --- |
| Gross Profit Margin | (Net Sales - COGS*) / Net Sales x 100 *COGS = Inventory Cost Per Unit x Quantity | Q1 - Profitability by product |
| Net Sales | Sum of Net Sales column (after discounts applied) | Q1, Q2 |
| Discount Rate | Average Discount % across orders; flag categories with unusually high discounting | Q1 - Profitability |
| Month-over-Month Growth | (Current Month Sales - Prior Month Sales) / Prior Month Sales x 100 | Q2 - Sales trends |
| On-Time Delivery Rate | Orders where Delay Shipment = 0 / Total Orders x 100 | Q3 - Shipment performance |
| Average Fulfillment Days | Mean of Warehouse Order Fulfillment (days) column per product / region | Q3 - Shipment performance |
| Total Storage Cost | Sum of Storage Cost per product per month; trended over time | Q4 - Inventory efficiency |
| Storage Cost per Unit | Storage Cost / Warehouse Inventory; flags high-burden SKUs | Q4 - Inventory efficiency |
| Inventory Turnover Proxy | Net Sales / Average Warehouse Inventory value for the period | Q4 - Inventory efficiency |
| Order Volume by Market | Count of orders segmented by Customer Market and Customer Region | Q5 - Market segmentation |
| Revenue by Region | Sum of Net Sales grouped by Customer Region and Customer Province | Q5 - Market segmentation |

7.  Tools & Workflow

| Tool | Role in Workflow | Output |
| --- | --- | --- |
| Microsoft Excel | Phase 1 - Data cleaning, quality audit, and preparation. Identify and resolve all data quality issues before analysis begins. | Clean, validated dataset ready for import |
| Microsoft Power BI | Phase 2 - Data modelling, DAX measure creation, relationship management, and dashboard build. | Two interactive dashboards |
| Power BI Service | Phase 3 - (Optional) Publish dashboards for stakeholder access via browser without requiring Power BI Desktop. | Shareable dashboard links |

Workflow Sequence

- Data audit in Excel - Profile each table, document all quality issues found.

- Data cleaning in Excel - Resolve all issues identified in the audit (duplicates, nulls, format inconsistencies, calculation errors).

- Import to Power BI - Load the cleaned dataset, build the data model, and define table relationships.

- DAX measures - Write calculated measures for all metrics defined in Section 6.

- Dashboard build - Design and build both dashboards per the deliverable specs in Section 8.

- Review and publish - Review outputs for accuracy, finalize formatting, and publish.

8.  Deliverables

| Deliverable | Audience | Contents | Purpose |
| --- | --- | --- | --- |
| Executive Dashboard | VP of Operations / Senior Leadership | Total revenue, profit margin by product and category, MoM and YoY sales trends, regional revenue performance, on-time delivery rate summary | Enables leadership to monitor overall business health and identify top and bottom performing products at a glance |
| Inventory Management Dashboard | Warehouse Manager | Monthly inventory levels by SKU and category, storage cost trends, fulfillment days by product, delayed shipment breakdown by region and category | Enables the warehouse team to identify high-cost inventory lines, monitor fulfillment speed, and prioritize delay reduction efforts |
| Clean Dataset (Excel) | Internal / Portfolio | The fully cleaned and validated Excel workbook used as the source for all analysis | Documents the data cleaning process and serves as a reproducible data foundation |
| Project Write-Up | Portfolio / Hiring Managers | Summary of business problem, methodology, key findings, and recommendations - written as a LinkedIn article or portfolio case study | Demonstrates end-to-end analytical thinking to prospective employers and clients |

9.  Assumptions & Constraints

Assumptions

- COGS is approximated as Inventory Cost Per Unit multiplied by order Quantity. A full cost accounting model is not available for this dataset.

- Orders with negative quantities are treated as product returns and will be excluded from profitability calculations unless otherwise noted.

- Customer IDs with formatting inconsistencies refer to the same customers and will be standardized during cleaning.

- The dataset is a representative sample of real warehouse operations; absolute dollar values are illustrative, not audited financials.

Constraints

- No real-time data connection is available; the dataset is a static export covering January 2023 to December 2025.

- Supplier cost data and production overhead are not included; profitability analysis is limited to what can be derived from the available fields.

- Customer-level segmentation is limited to region, province, and market type; individual customer behaviour analysis is not possible without additional PII.

10.  Success Criteria

This project will be considered complete and successful when the following criteria are met:

- All five analytical questions defined in Section 5 are answered with supporting data visualizations.

- Both dashboards are interactive, accurately reflect the cleaned dataset, and are free of calculation errors.

- The Executive Dashboard can be understood by a non-technical stakeholder within 60 seconds of opening it.

- The Inventory Dashboard provides enough granularity for the Warehouse Manager to act on specific SKUs or regions without additional analysis.

- A written project summary suitable for a portfolio or LinkedIn article is produced alongside the dashboards.

Document prepared by Maj Okrikri  |  May 2026  |  Version 1.0